## Import from RTC
Type | Id | Status | Priority | Severity | Summary | Owned By | Created By
Task | 1 | Done | Unassigned | Normal | Define a new build | Niek Vandael | Niek Vandael
Task | 2 | Done | Unassigned | Normal | Share code with Jazz Source Control | Niek Vandael | Niek Vandael
Task | 3 | Done | Unassigned | Normal | Define sprints/iterations | Niek Vandael | Niek Vandael
Task | 4 | Done | Unassigned | Normal | Define categories and releases for work items | Niek Vandael | Niek Vandael
Task | 5 | Done | Unassigned | Normal | Define team members | Niek Vandael | Niek Vandael
Task | 6 | Done | Unassigned | Normal | Define permissions | Niek Vandael | Niek Vandael
Task | 7 | Done | High | Normal | Setup RTC | Niek Vandael | Niek Vandael
Task | 8 | Done | High | Normal | Setup RedHat Cloud | Niek Vandael | Niek Vandael
Task | 9 | Done | Unassigned | Major | Share initial code | Niek Vandael | Niek Vandael
Task | 10 | Done | Unassigned | Normal | Setup Openshift Server | Jesse Vranken | Jesse Vranken
Task | 11 | Done | Unassigned | Minor | RTC Testing | Jesse Vranken | Jesse Vranken
Task | 12 | Done | Unassigned | Normal | Enable Jenkins | Niek Vandael | Niek Vandael
Task | 13 | Done | Unassigned | Normal | [Joining a Team] Create a Repository Workspace | Dennie Grondelaers | Niek Vandael
Task | 14 | Done | Unassigned | Normal | [Joining a Team] Find Your Work Items | Dennie Grondelaers | Niek Vandael
Task | 15 | Done | Unassigned | Normal | [Joining a Team] Set Up Instant Messaging | Dennie Grondelaers | Niek Vandael
Task | 16 | Done | Unassigned | Normal | [Joining a Team] Create a Repository Workspace | Bart Hunerbein | Niek Vandael
Task | 17 | Done | Unassigned | Normal | [Joining a Team] Find Your Work Items | Bart Hunerbein | Niek Vandael
Task | 18 | Done | Unassigned | Normal | [Joining a Team] Set Up Instant Messaging | Bart Hunerbein | Niek Vandael
Task | 19 | Done | Unassigned | Normal | [Joining a Team] Create a Repository Workspace | Arjen Schuurman | Niek Vandael
Task | 20 | Done | Unassigned | Normal | [Joining a Team] Find Your Work Items | Arjen Schuurman | Niek Vandael
Task | 21 | Done | Unassigned | Normal | [Joining a Team] Set Up Instant Messaging | Arjen Schuurman | Niek Vandael
Story | 22 | Invalid | Unassigned | Normal | Create Analisis | Unassigned | Niek Vandael
Task | 23 | Done | Unassigned | Normal | Analyse login | Unassigned | Niek Vandael
Task | 24 | Done | Unassigned | Normal | Analyse projects | Unassigned | Niek Vandael
Task | 25 | Done | Unassigned | Normal | Analyse subscribers | Unassigned | Niek Vandael
Task | 26 | Done | Unassigned | Normal | Set Up Project Structure | Jesse Vranken | Jesse Vranken
Story | 27 | In Progress | High | Normal | Analyse maken | Niek Vandael | Bart Hunerbein
Task | 28 | In Progress | High | Normal | Use case diagrams maken | Unassigned | Niek Vandael
Task | 29 | In Progress | High | Normal | Vereisten verzamelen | Jesse Vranken | Jesse Vranken
Task | 30 | In Progress | Medium | Normal | Plan van aanpak | Jesse Vranken | Jesse Vranken
Task | 31 | Invalid | High | Normal | Create Use Cases Diagram | Jesse Vranken | Jesse Vranken
Task | 32 | Done | Medium | Normal | Testen van de deliveries | Niek Vandael | Niek Vandael
Task | 33 | Done | Unassigned | Major | RTC setup development environment documentje maken | Niek Vandael | Niek Vandael
Story | 34 | Done | High | Normal | Setup development environment | Niek Vandael | Niek Vandael
Story | 35 | New | High | Normal | Fill in "Plan van aanpak" | Unassigned | Niek Vandael
Story | 36 | New | High | Normal | Requirements opstellen | Arjen Schuurman | Niek Vandael
Story | 37 | New | Unassigned | Normal | Studenten en docenten moeten inloggen alvorens de applicatie te kunnen gebruiken | Unassigned | Niek Vandael
Task | 38 | Done | Medium | Normal | Setup Openshift | Jesse Vranken | Niek Vandael
Task | 39 | Done | Unassigned | Normal | setup Eclipse with RTC | Unassigned | Niek Vandael
Story | 40 | New | Unassigned | Normal | Studenten kunnen projecten liken | Unassigned | Niek Vandael
Story | 41 | New | Unassigned | Normal | Studenten kunnen op projecten inschrijven | Unassigned | Niek Vandael
Story | 42 | New | Unassigned | Normal | Docenten kunnen op projecten intekenen | Unassigned | Niek Vandael
Story | 43 | New | Unassigned | Normal | Docenten kunnen projecten goedkeuren | Unassigned | Niek Vandael
Story | 44 | New | Unassigned | Normal | Docenten kunnen een aanvraag indien voor ondersteuning van andere docenten | Unassigned | Niek Vandael
Story | 45 | New | Unassigned | Normal | Technische details zoals video en foto-hosting uitzoeken | Unassigned | Niek Vandael
Story | 46 | New | Unassigned | Normal | Mockups maken | Bart Hunerbein | Niek Vandael
Story | 47 | New | Unassigned | Normal | Docenten/studenten kunnen de pagina sorteren op basis van tags/likes | Unassigned | Niek Vandael
Story | 48 | New | Unassigned | Normal | Studenten moeten projecten kunnen maken gerelateerd aan bepaalde categorieen | Unassigned | Niek Vandael
Story | 49 | New | High | Normal | Use cases opstellen | Unassigned | Niek Vandael
Story | 50 | New | Unassigned | Normal | Klassediagrammen maken | Jesse Vranken | Niek Vandael
Story | 51 | New | Unassigned | Normal | Sequentiediagram opstellen | Unassigned | Niek Vandael
Story | 52 | New | Unassigned | Normal | Voorbereiding verdediging eindversie | Unassigned | Niek Vandael
Story | 53 | New | Unassigned | Normal | Voorbereiding presentatie (engels) | Unassigned | Niek Vandael
Story | 54 | New | Unassigned | Normal | Administor moet alles kunnen wijzigen | Unassigned | Niek Vandael
Story | 55 | Invalid | Unassigned | Normal | blabla | Unassigned | Niek Vandael
Task | 56 | New | Unassigned | Normal | backend uitwerken | Unassigned | Niek Vandael
Task | 57 | In Progress | Unassigned | Major | ERD maken | Niek Vandael | Niek Vandael
Task | 58 | In Progress | Unassigned | Normal | Use case diagram studenten | Niek Vandael | Niek Vandael
Story | 59 | New | Medium | Normal | Departement per student/docent toevoegen | Bart Hunerbein | Niek Vandael
Task | 60 | Done | Unassigned | Major | Create DFDs | Niek Vandael | Niek Vandael
Task | 61 | In Progress | Low | Unclassified | Questions to ask | Bart Hunerbein | Bart Hunerbein
Task | 62 | New | Unassigned | Normal | Create Domain Model | Jesse Vranken | Jesse Vranken
Task | 63 | New | Unassigned | Normal | Create Activity Diagram | Jesse Vranken | Jesse Vranken
Task | 64 | New | Unassigned | Normal | Create Class Diagram Domain | Jesse Vranken | Jesse Vranken
Task | 65 | New | Unassigned | Normal | First project setup (Angular) | Niek Vandael | Niek Vandael
Task | 66 | New | Unassigned | Normal | Testing Angular | Jesse Vranken | Jesse Vranken
Task | 67 | New | Unassigned | Normal | Implement model | Jesse Vranken | Jesse Vranken
Task | 68 | New | Unassigned | Normal | Test Model | Jesse Vranken | Jesse Vranken
Task | 69 | New | Unassigned | Normal | Implement Services | Jesse Vranken | Jesse Vranken
Task | 70 | New | Unassigned | Major | Create Project list | Niek Vandael | Niek Vandael
Task | 71 | New | Unassigned | Major | Automate MySQL entries on table-creation | Niek Vandael | Niek Vandael
Defect | 72 | Resolved | Unassigned | Normal | RestControllers unavailable after implementing JpaRepository | Niek Vandael | Niek Vandael
Task | 73 | New | Unassigned | Normal | Configure MySQL Database | Niek Vandael | Niek Vandael
Defect | 74 | Reopened | Unassigned | Normal | Openshift does not build anymore | Niek Vandael | Niek Vandael
Task | 75 | New | Unassigned | Normal | Angular - Implement Likes | Jesse Vranken | Jesse Vranken
Task | 76 | In Progress | Unassigned | Normal | Toggle likes for a project | Niek Vandael | Niek Vandael
Task | 77 | New | Unassigned | Normal | Spring-boot setup and configuration | Dennie Grondelaers | Dennie Grondelaers
Task | 78 | New | Unassigned | Normal | Angular - Implement Project Service | Jesse Vranken | Jesse Vranken
Task | 79 | New | Unassigned | Normal | English presentation | Niek Vandael | Niek Vandael
Task | 80 | New | Unassigned | Normal | Spring - Implement Subscriber Student Service | Jesse Vranken | Jesse Vranken
Task | 81 | New | Unassigned | Normal | Angular - Implement Subscriber Student Service | Jesse Vranken | Jesse Vranken
Task | 82 | New | Unassigned | Normal | Spring - Implement Subscriber Docent Service | Jesse Vranken | Jesse Vranken
Defect | 83 | New | Unassigned | Minor | MySql timeout after 8 hours | Niek Vandael | Niek Vandael
Task | 84 | New | Unassigned | Normal | Security setup | Dennie Grondelaers | Dennie Grondelaers
Task | 85 | New | Unassigned | Normal | Create category screen | Niek Vandael | Niek Vandael
Defect | 86 | New | Unassigned | Critical | Security - Autowiring Error | Jesse Vranken | Jesse Vranken
Task | 87 | New | Unassigned | Normal | Save youtube videos on project | Niek Vandael | Niek Vandael
Task | 88 | New | Unassigned | Normal | Add pictures on project | Niek Vandael | Niek Vandael
Task | 89 | New | Unassigned | Normal | Enable update for projects | Arjen Schuurman | Arjen Schuurman
Task | 90 | New | Unassigned | Normal | Resource (view model) fuctionality | Dennie Grondelaers | Dennie Grondelaers
Task | 91 | Done | Unassigned | Normal | Add milestones to project | Niek Vandael | Niek Vandael
Task | 92 | Done | Unassigned | Normal | Autofill status, lastupdate and last updated by when persisting an entity | Niek Vandael | Niek Vandael
Task | 93 | Done | Unassigned | Normal | Create department list | Niek Vandael | Niek Vandael
Task | 94 | Done | Unassigned | Normal | Add wanted-subscribers to project | Niek Vandael | Niek Vandael
Task | 95 | New | Unassigned | Normal | Angular - Implement Subscriber Docent Service | Jesse Vranken | Jesse Vranken
Task | 96 | New | Unassigned | Normal | Prezis toevoegen aan het project | Jesse Vranken | Jesse Vranken
Task | 97 | New | Unassigned | Normal | Search functionality (angular) | Bart Hunerbein | Bart Hunerbein
Task | 98 | New | Unassigned | Normal | Online bestanden toevoegen aan het project | Jesse Vranken | Jesse Vranken
Defect | 99 | New | Unassigned | Normal | JSTD syntax error in eclipse | Niek Vandael | Niek Vandael
Task | 100 | Done | Unassigned | Normal | Compress pictures | Niek Vandael | Niek Vandael
Task | 101 | New | Unassigned | Normal | Add Category to projects | Niek Vandael | Niek Vandael
Task | 102 | Done | Unassigned | Normal | Filter projects by category | Niek Vandael | Niek Vandael
Defect | 103 | New | Unassigned | Normal | Form submits when not valid (new project) | Niek Vandael | Niek Vandael
Defect | 104 | New | Unassigned | Normal | logout triggers authentication error | Niek Vandael | Niek Vandael
Defect | 105 | New | Unassigned | Normal | Deleting category does not show errormessage | Niek Vandael | Niek Vandael
Defect | 106 | New | Unassigned | Normal | Missing menu item 'New project' | Niek Vandael | Niek Vandael
Task | 107 | New | Unassigned | Normal | Create domain model | Niek Vandael | Niek Vandael
Defect | 108 | Resolved | Unassigned | Normal | Disable like when not authenticated | Niek Vandael | Niek Vandael
Task | 109 | New | Unassigned | Normal | Layout myProject Page | Jesse Vranken | Jesse Vranken
Task | 110 | New | Unassigned | Normal | Add Background | Jesse Vranken | Jesse Vranken
Task | 111 | New | Unassigned | Normal | Layout home pagina | Jesse Vranken | Jesse Vranken
Task | 112 | New | Unassigned | Normal | Add domain to projects | Jesse Vranken | Jesse Vranken
Task | 113 | New | Medium | Normal | Remove comic sans font. | Arjen Schuurman | Arjen Schuurman
Defect | 114 | Resolved | Unassigned | Normal | Guests cannot view project details | Niek Vandael | Niek Vandael
Task | 115 | New | Medium | Normal | Align subscripe/backup row, move to detail project page. | Arjen Schuurman | Arjen Schuurman
Task | 116 | New | Unassigned | Normal | Plan van aanpak: Quality assurance | Niek Vandael | Niek Vandael
Task | 117 | Done | Unassigned | Normal | Search projects based on tags | Niek Vandael | Niek Vandael
Task | 118 | New | Unassigned | Normal | Tag projects (multiple categories per project) | Niek Vandael | Niek Vandael
Task | 119 | New | Unassigned | Normal | Create FIT criteria | Niek Vandael | Niek Vandael
Task | 120 | Done | Unassigned | Normal | Docenten kunnen filteren op niet-gebackte projecten | Niek Vandael | Niek Vandael
Task | 121 | New | Unassigned | Normal | Projectstatus direct zichtbaar voor studenten | Niek Vandael | Niek Vandael
Task | 122 | Done | Unassigned | Normal | Studenten kunnen projecten filteren waarop ze zich kunnen inschrijven | Niek Vandael | Niek Vandael
Task | 123 | New | Unassigned | Normal | Rework new project page/controller | Arjen Schuurman | Arjen Schuurman
Task | 124 | New | Unassigned | Normal | Verslag Meetings | Jesse Vranken | Jesse Vranken
Defect | 125 | Resolved | Unassigned | Normal | Bugfix subscribe/back project | Jesse Vranken | Jesse Vranken
Defect | 126 | Resolved | Unassigned | Normal | Bugfix Pictures not displaying on myprojects page | Jesse Vranken | Jesse Vranken
Task | 127 | New | Unassigned | Normal | Only show Student Subscribe when possible | Jesse Vranken | Jesse Vranken
Task | 128 | New | Unassigned | Normal | Layout Language Select | Jesse Vranken | Jesse Vranken
Task | 129 | New | Unassigned | Normal | Layout Login Button | Jesse Vranken | Jesse Vranken
Task | 130 | New | Unassigned | Normal | Layout - Adding All Caps for titles and subtitles | Jesse Vranken | Jesse Vranken
Defect | 131 | Resolved | Unassigned | Normal | Bugfix - Title not showing in public list | Jesse Vranken | Jesse Vranken
Task | 132 | New | Unassigned | Normal | Create project progressbar (backed/subscribed) | Niek Vandael | Niek Vandael
Defect | 133 | New | Unassigned | Normal | Session lost after refresh | Niek Vandael | Niek Vandael
Defect | 134 | Resolved | Unassigned | Normal | Bugfix Delete Media | Jesse Vranken | Jesse Vranken
Task | 135 | New | Unassigned | Normal | Only show docent back when possible | Jesse Vranken | Jesse Vranken
Defect | 136 | Resolved | Unassigned | Normal | Bugfix - import sql | Jesse Vranken | Jesse Vranken
Task | 137 | New | Unassigned | Normal | Show Docent backed projects in myprojects | Jesse Vranken | Jesse Vranken
Task | 138 | New | Unassigned | Normal | Change max number of media to 100 | Jesse Vranken | Jesse Vranken
Task | 139 | New | Unassigned | Normal | Add social media buttons | Niek Vandael | Niek Vandael
Task | 140 | New | Unassigned | Normal | Enable student subscribe when project is fully backed | Jesse Vranken | Jesse Vranken
Defect | 141 | New | Unassigned | Normal | Bugfix - filter for student home page | Jesse Vranken | Jesse Vranken
Task | 142 | New | Unassigned | Normal | Add comments to projects | Niek Vandael | Niek Vandael
Defect | 143 | New | Unassigned | Minor | Show only first picture in project list | Niek Vandael | Niek Vandael
Task | 144 | New | Medium | Normal | Create popup messages for result while saving/creating categories. | Arjen Schuurman | Arjen Schuurman
Task | 145 | New | Medium | Normal | Create popup messages for result while saving/creating projects. | Arjen Schuurman | Arjen Schuurman
Defect | 146 | Resolved | Unassigned | Normal | Bugfix - error updating projects | Jesse Vranken | Jesse Vranken
Task | 147 | New | Unassigned | Normal | Only docents can make projects public | Jesse Vranken | Jesse Vranken
Task | 148 | New | Unassigned | Normal | Picture carousel on detail page | Niek Vandael | Niek Vandael
Task | 149 | New | Unassigned | Normal | Disable comments for public | Jesse Vranken | Jesse Vranken
Task | 150 | New | Unassigned | Normal | Disable student edit for backed projects | Jesse Vranken | Jesse Vranken
Defect | 151 | Resolved | Unassigned | Normal | Docents can't back anymore | Jesse Vranken | Jesse Vranken
Task | 152 | New | Unassigned | Normal | Detail page styling | Niek Vandael | Niek Vandael
Task | 153 | New | Unassigned | Normal | Set start date when 100% subscribed | Jesse Vranken | Jesse Vranken
Defect | 154 | Resolved | Unassigned | Normal | No progressbar showing on 0pct | Niek Vandael | Niek Vandael
Task | 155 | New | Unassigned | Normal | Allow Docents to edit all projects | Jesse Vranken | Jesse Vranken
Task | 156 | New | Unassigned | Normal | Allow Docents do delete all projects | Jesse Vranken | Jesse Vranken
Task | 157 | New | Unassigned | Normal | Display end date & duration | Jesse Vranken | Jesse Vranken
Defect | 158 | Resolved | Unassigned | Normal | No text on full progressbar | Jesse Vranken | Jesse Vranken
Task | 159 | New | Medium | Normal | Update project detail page | Arjen Schuurman | Arjen Schuurman
Task | 160 | New | Unassigned | Normal | Get archived projects | Niek Vandael | Niek Vandael
Task | 161 | New | Unassigned | Normal | Using preziId from backend | Jesse Vranken | Jesse Vranken
Task | 162 | New | Unassigned | Normal | Add Scrollbar for long description | Jesse Vranken | Jesse Vranken
Task | 163 | New | Unassigned | Normal | Docents can delete subscribers | Jesse Vranken | Jesse Vranken
Defect | 164 | Resolved | Unassigned | Normal | Only show make new.. when project is new | Jesse Vranken | Jesse Vranken
Defect | 165 | New | Unassigned | Normal | Disable animation on progress bar | Niek Vandael | Niek Vandael
Defect | 166 | Resolved | Unassigned | Normal | Show full project description without scroller | Niek Vandael | Niek Vandael
Defect | 167 | Resolved | Unassigned | Normal | BackingPct not centered when > 100 | Niek Vandael | Niek Vandael
Defect | 168 | Resolved | Unassigned | Normal | Change background color to match selected menu item | Niek Vandael | Niek Vandael
Defect | 169 | Resolved | Unassigned | Normal | Project save should return to project detail | Niek Vandael | Niek Vandael
Defect | 170 | New | Unassigned | Normal | Left title should navigate to home page | Niek Vandael | Niek Vandael
Task | 171 | Done | Unassigned | Normal | Possibility to delete a project comment | Niek Vandael | Niek Vandael
Defect | 172 | Resolved | Unassigned | Normal | Like function is broken | Niek Vandael | Niek Vandael
Defect | 173 | Resolved | Unassigned | Normal | About page not presentable | Niek Vandael | Niek Vandael
Defect | 174 | Resolved | Unassigned | Normal | Search by tag or keyword in one search box | Niek Vandael | Niek Vandael
Defect | 175 | Resolved | Unassigned | Normal | Category menuitem not showing 'active' | Niek Vandael | Niek Vandael
Task | 176 | New | Unassigned | Normal | Show icon when project is 'running' | Niek Vandael | Niek Vandael
Task | 177 | New | Unassigned | Normal | Make project title bold | Jesse Vranken | Jesse Vranken
Task | 178 | New | Unassigned | Normal | Allow Back after 100% | Jesse Vranken | Jesse Vranken
Task | 179 | New | Unassigned | Normal | make public only when 100% backed | Jesse Vranken | Jesse Vranken
Task | 180 | New | Unassigned | Normal | Navigate to details on title click | Jesse Vranken | Jesse Vranken
Task | 181 | New | Unassigned | Normal | Text back > steun(nl), support(en) | Jesse Vranken | Jesse Vranken
Task | 182 | New | Unassigned | Normal | Show full start/end time | Jesse Vranken | Jesse Vranken
Task | 183 | New | Unassigned | Normal | Text adjustment for Docent filter | Jesse Vranken | Jesse Vranken
Task | 184 | New | Unassigned | Normal | Layout Project Block | Jesse Vranken | Jesse Vranken
Task | 185 | New | Unassigned | Normal | Prevent request manipulation | Jesse Vranken | Jesse Vranken
Task | 186 | New | Unassigned | Normal | Show text when list is empty | Jesse Vranken | Jesse Vranken
Task | 187 | New | Unassigned | Normal | Popup message on back/subcsribe | Jesse Vranken | Jesse Vranken
Task | 188 | New | Unassigned | Normal | Project form validation | Jesse Vranken | Jesse Vranken
Task | 189 | New | Unassigned | Normal | Search on more fields | Jesse Vranken | Jesse Vranken
Task | 190 | New | Unassigned | Normal | Docents can delete supporters | Jesse Vranken | Jesse Vranken
Task | 191 | New | Unassigned | Normal | Redirect on cancel edit | Jesse Vranken | Jesse Vranken
Task | 192 | New | Medium | Normal | Add logo to menu | Arjen Schuurman | Arjen Schuurman
Task | 193 | New | High | Normal | Improve menu bar to show correct on small screen size. | Arjen Schuurman | Arjen Schuurman
Task | 194 | New | Unassigned | Normal | Show favicon | Jesse Vranken | Jesse Vranken
Task | 195 | New | Unassigned | Normal | Model Validation | Jesse Vranken | Jesse Vranken
Task | 196 | New | High | Normal | Incorrect layout when adding items on new project page, especially on smaller screen sizes | Arjen Schuurman | Arjen Schuurman
Task | 197 | New | Medium | Normal | Add error toast for delete constraint by categories | Arjen Schuurman | Arjen Schuurman
Task | 198 | New | Unassigned | Normal | Add Javadoc | Jesse Vranken | Jesse Vranken
Task | 199 | New | Unassigned | Normal | Add duration options | Jesse Vranken | Jesse Vranken
Task | 200 | New | Unassigned | Normal | Code convention adjustments | Jesse Vranken | Jesse Vranken
Task | 201 | New | Unassigned | Normal | Order projects on number of likes | Jesse Vranken | Jesse Vranken
Task | 202 | New | Medium | Normal | Adjust detail page | Arjen Schuurman | Arjen Schuurman

## Time spent by user
| Workitem |  | Niek Vandael | Jesse Vranken | Arjen Schuurman | Dennie Grondelars | Bart Hunerbein | Total
Defect | Resource (view model) fuctionality | Dennie Grondelaers |  |  |  | 4
Defect | Autofill status, lastupdate and last updated by when persisting an entity | Niek Vandael | 1
Defect | Add Category to projects | Niek Vandael | 1
Defect | logout triggers authentication error | Niek Vandael
Defect | Search projects based on tags | Niek Vandael | 2
Defect | Projectstatus direct zichtbaar voor studenten | Niek Vandael | 1
Defect | Studenten kunnen projecten filteren waarop ze zich kunnen inschrijven | Niek Vandael | 2
Defect | Rework new project page/controller | Arjen Schuurman |  |  | 3
Defect | Verslag Meetings | Jesse Vranken |  | 1
Defect | Bugfix Pictures not displaying on myprojects page | Jesse Vranken |  | 0.5
Defect | Create project progressbar (backed/subscribed) | Niek Vandael | 1
Defect | Show only first picture in project list | Niek Vandael | 1
Defect | Create popup messages for result while saving/creating categories. | Arjen Schuurman |  |  | 3
Defect | Disable comments for public | Jesse Vranken |  | 0.25
Defect | Docents can't back anymore | Jesse Vranken |  | 0.5
Defect | Detail page styling | Niek Vandael
Defect | No progressbar showing on 0pct | Niek Vandael | 1
Defect | Update project detail page | Arjen Schuurman |  |  | 4
Defect | Using preziId from backend | Jesse Vranken |  | 1
Defect | Only show make new.. when project is new | Jesse Vranken |  | 0.25
Defect | Project save should return to project detail | Niek Vandael | 1
Defect | Like function is broken | Niek Vandael | 2
Defect | Show icon when project is 'running' | Niek Vandael | 2
Defect | Show full start/end time | Jesse Vranken |  | 0.25
Defect | Text adjustment for Docent filter | Jesse Vranken |  | 0.25
Defect | Layout Project Block | Jesse Vranken |  | 0.5
Defect | Prevent request manipulation | Jesse Vranken |  | 2
Defect | Show text when list is empty | Jesse Vranken |  | 1
Defect | Popup message on back/subcsribe | Jesse Vranken |  | 0.25
Defect | Project form validation | Jesse Vranken |  | 0.5
Defect | Docents can delete supporters | Jesse Vranken |  | 1
Defect | Redirect on cancel edit | Jesse Vranken |  | 0.25
Defect | Add logo to menu | Arjen Schuurman |  |  | 1
Defect | Improve menu bar to show correct on small screen size. | Arjen Schuurman |  |  | 2
Time spent on defects |  |  | 15 | 9.5 | 13 | 4 | 0 | 41.5
Task | Define a new build | Niek Vandael | 5
Task | Share code with Jazz Source Control | Niek Vandael | 1
Task | Define sprints/iterations | Niek Vandael | 1
Task | Define categories and releases for work items | Niek Vandael | 1
Task | Define team members | Niek Vandael | 1
Task | Define permissions | Niek Vandael | 0
Task | Setup RTC | Niek Vandael | 8
Task | Share initial code | Niek Vandael | 0 | 5
Task | Setup Openshift Server | Jesse Vranken | 10 | 15
Task | RTC Testing | Jesse Vranken | 2 | 2
Task | Enable Jenkins | Niek Vandael | 2 | 15
Task | Create Analisis | Unassigned | 10 | 10 | 10 | 10 | 10
Task | Analyse login | Unassigned |  |  | 5 | 5
Task | Analyse projects | Unassigned | 5
Task | Analyse subscribers | Unassigned |  | 5
Task | Set Up Project Structure | Jesse Vranken |  | 3 | 5 | 3
Task | Vereisten verzamelen | Jesse Vranken | 2 | 2 | 2 | 2 | 1
Task | Plan van aanpak | Jesse Vranken | 4 | 5 | 8 | 2 | 2
Task | Create Use Cases Diagram | Jesse Vranken | 15 | 2
Task | RTC setup development environment documentje maken | Niek Vandael | 1
Task | Setup development environment | Niek Vandael | 1 | 1
Task | Requirements opstellen | Arjen Schuurman | 1 | 2 | 5 | 2 | 2
Task | Studenten en docenten moeten inloggen alvorens de applicatie te kunnen gebruiken | Unassigned |  | 1 | 2 | 15
Task | Studenten kunnen projecten liken | Unassigned | 2 |  | 2
Task | Studenten kunnen op projecten inschrijven | Unassigned |  | 5
Task | Docenten kunnen op projecten intekenen | Unassigned |  | 5
Task | Technische details zoals video en foto-hosting uitzoeken | Unassigned |  | 1 | 3 | 2
Task | Mockups maken | Bart Hunerbein |  |  |  |  | 3
Task | Voorbereiding presentatie (engels) | Unassigned | 2 | 2 | 2 | 2
Task | backend uitwerken | Unassigned |  | 10 |  | 5
Task | Openshift does not build anymore | Niek Vandael | 3 | 3
Task | Angular - Implement Likes | Jesse Vranken |  | 1
Task | Toggle likes for a project | Niek Vandael | 3
Task | Angular - Implement Project Service | Jesse Vranken |  | 2
Task | English presentation | Niek Vandael | 1 | 1 | 1 | 1
Task | Spring - Implement Subscriber Student Service | Jesse Vranken |  | 1
Task | Angular - Implement Subscriber Student Service | Jesse Vranken |  | 1
Task | Spring - Implement Subscriber Docent Service | Jesse Vranken |  | 1
Task | MySql timeout after 8 hours | Niek Vandael | 1
Task | Security setup | Dennie Grondelaers |  |  | 10 | 10
Task | Create category screen | Niek Vandael | 4 |  | 2
Task | Security - Autowiring Error | Jesse Vranken |  | 0.5
Task | Save youtube videos on project | Niek Vandael | 3
Task | Add pictures on project | Niek Vandael | 2
Task | Enable update for projects | Arjen Schuurman |  |  | 3
Task | Add milestones to project | Niek Vandael | 1
Task | Create department list | Niek Vandael | 1
Task | Add wanted-subscribers to project | Niek Vandael | 2
Task | Angular - Implement Subscriber Docent Service | Jesse Vranken |  | 1
Task | Prezis toevoegen aan het project | Jesse Vranken |  | 0.5
Task | Search functionality (angular) | Bart Hunerbein |  |  |  |  | 2
Task | Online bestanden toevoegen aan het project | Jesse Vranken |  | 1
Task | JSTD syntax error in eclipse | Niek Vandael | 1
Task | Compress pictures | Niek Vandael | 3
Task | Filter projects by category | Niek Vandael | 1
Task | Form submits when not valid (new project) | Niek Vandael | 1
Task | Deleting category does not show errormessage | Niek Vandael | 1
Task | Missing menu item 'New project' | Niek Vandael | 1
Task | Create domain model | Niek Vandael | 1
Task | Disable like when not authenticated | Niek Vandael | 1
Task | Layout myProject Page | Jesse Vranken |  | 1
Task | Add Background | Jesse Vranken |  | 0.25
Task | Layout home pagina | Jesse Vranken |  | 0.5
Task | Add domain to projects | Jesse Vranken |  | 1
Task | Remove comic sans font. | Arjen Schuurman |  |  | 0.25
Task | Guests cannot view project details | Niek Vandael | 1
Task | Align subscripe/backup row, move to detail project page. | Arjen Schuurman |  |  | 2
Task | Plan van aanpak: Quality assurance | Niek Vandael | 5 | 3 | 1 | 1
Task | Tag projects (multiple categories per project) | Niek Vandael | 4
Task | Create FIT criteria | Niek Vandael | 2 |  |  | 2
Task | Docenten kunnen filteren op niet-gebackte projecten | Niek Vandael | 1
Task | Bugfix subscribe/back project | Jesse Vranken |  | 1
Task | Only show Student Subscribe when possible | Jesse Vranken |  | 1
Task | Layout Language Select | Jesse Vranken |  | 1
Task | Layout Login Button | Jesse Vranken |  | 1
Task | Layout - Adding All Caps for titles and subtitles | Jesse Vranken |  | 1
Task | Bugfix - Title not showing in public list | Jesse Vranken |  | 1
Task | Session lost after refresh | Niek Vandael | 1
Task | Bugfix Delete Media | Jesse Vranken |  | 1
Task | Only show docent back when possible | Jesse Vranken |  | 1
Task | Bugfix - import sql | Jesse Vranken |  | 1
Task | Show Docent backed projects in myprojects | Jesse Vranken |  | 1
Task | Change max number of media to 100 | Jesse Vranken |  | 1
Task | Add social media buttons | Niek Vandael
Task | Enable student subscribe when project is fully backed | Jesse Vranken |  | 1
Task | Bugfix - filter for student home page | Jesse Vranken |  | 1
Task | Add comments to projects | Niek Vandael | 3
Task | Create popup messages for result while saving/creating projects. | Arjen Schuurman |  |  | 2
Task | Bugfix - error updating projects | Jesse Vranken |  | 1
Task | Only docents can make projects public | Jesse Vranken |  | 1
Task | Picture carousel on detail page | Niek Vandael | 2
Task | Disable student edit for backed projects | Jesse Vranken |  | 1
Task | Set start date when 100% subscribed | Jesse Vranken |  | 1
Task | Allow Docents to edit all projects | Jesse Vranken |  | 1
Task | Allow Docents do delete all projects | Jesse Vranken |  | 1
Task | Display end date & duration | Jesse Vranken |  | 1
Task | No text on full progressbar | Jesse Vranken |  | 1
Task | Get archived projects | Niek Vandael | 0.5
Task | Add Scrollbar for long description | Jesse Vranken |  | 1
Task | Docents can delete subscribers | Jesse Vranken |  | 1
Task | Disable animation on progress bar | Niek Vandael | 1
Task | Show full project description without scroller | Niek Vandael | 1
Task | BackingPct not centered when > 100 | Niek Vandael | 1
Task | Change background color to match selected menu item | Niek Vandael | 1
Task | Left title should navigate to home page | Niek Vandael | 1
Task | Possibility to delete a project comment | Niek Vandael | 1
Task | About page not presentable | Niek Vandael | 1
Task | Search by tag or keyword in one search box | Niek Vandael | 4
Task | Category menuitem not showing 'active' | Niek Vandael | 1
Task | Make project title bold | Jesse Vranken |  | 1
Task | Allow Back after 100% | Jesse Vranken |  | 1
Task | make public only when 100% backed | Jesse Vranken |  | 1
Task | Navigate to details on title click | Jesse Vranken |  | 1
Task | Text back > steun(nl), support(en) | Jesse Vranken |  | 1
Task | Search on more fields | Jesse Vranken |  | 1
Task | Show favicon | Jesse Vranken |  | 1
Task | Model Validation | Jesse Vranken |  | 1
Task | Incorrect layout when adding items on new project page, especially on smaller screen sizes | Arjen Schuurman |  |  | 3
Task | Add error toast for delete constraint by categories | Arjen Schuurman |  |  | 1
Task | Add Javadoc | Jesse Vranken |  | 1
Task | Add duration options | Jesse Vranken |  | 1
Task | Code convention adjustments | Jesse Vranken |  | 1
Task | Order projects on number of likes | Jesse Vranken |  | 1
Task | setup Eclipse with RTC | Unassigned | 2 | 2 | 2 | 2 | 2
Task | Docenten/studenten kunnen de pagina sorteren op basis van tags/likes | Unassigned | 5 | 2 |  | 3
Task | Studenten moeten projecten kunnen maken gerelateerd aan bepaalde categorieen | Unassigned | 5 | 1 |  | 2
Task | Klassediagrammen maken | Jesse Vranken |  | 10
Task | Voorbereiding verdediging eindversie | Unassigned
Task | ERD maken | Niek Vandael |  | 5 |  | 2
Task | Use case diagram studenten | Niek Vandael | 2 | 1
Task | Departement per student/docent toevoegen | Bart Hunerbein | 2
Task | Create DFDs | Niek Vandael | 10
Task | Create Domain Model | Jesse Vranken |  | 5
Task | Create Activity Diagram | Jesse Vranken | 3
Task | Create Class Diagram Domain | Jesse Vranken | 4 | 4
Task | First project setup (Angular) | Niek Vandael | 1 | 1 | 24
Task | Testing Angular | Jesse Vranken |  | 1
Task | Implement model | Jesse Vranken |  | 5
Task | Test Model | Jesse Vranken |  | 1
Task | Implement Services | Jesse Vranken |  | 12
Task | Create Project list | Niek Vandael | 1
Task | Automate MySQL entries on table-creation | Niek Vandael | 1 | 1
Task | RestControllers unavailable after implementing JpaRepository | Niek Vandael | 1
Task | Configure MySQL Database | Niek Vandael | 1 | 1
Task | Spring-boot setup and configuration | Dennie Grondelaers |  |  |  | 10
Task | Testen van de deliveries | Niek Vandael | 5 | 5 |  | 2
Task | Adjust detail page | Arjen Schuurman |  |  | 4 | 1
Task | Unit testing | Dennie Grondelaers |  |  |  | 12
Time spent on tasks |  |  | 179.5 | 201.75 | 99.25 | 96 | 22 | 598.5
Total time spent |  |  | 194.5 | 211.25 | 112.25 | 100 | 22 | 640

## Total time spent
Team member | Niek Vandael | Jesse Vranken | Arjen Schuurman | Dennie Grondelars | Bart Hunerbein
Total time spent | 194.5 | 211.25 | 112.25 | 100 | 22

## Time spend on tasks
Team member | Niek Vandael | Jesse Vranken | Arjen Schuurman | Dennie Grondelars | Bart Hunerbein
Time spent on tasks | 179.5 | 201.75 | 99.25 | 96 | 22

## Time spend on defects
Team member | Niek Vandael | Jesse Vranken | Arjen Schuurman | Dennie Grondelars | Bart Hunerbein
Time spent on defects | 15 | 9.5 | 13 | 4 | 0

## Time spend by type
Type | Defect | Task
Time spend by type | 41.5 | 598.5

## Project cost
| Niek Vandael | Jesse Vranken | Arjen Schuurman | Dennie Grondelars | Bart Hunerbein
Time spent | 194.5 | 211.25 | 112.25 | 100 | 22
Hourly rate | 20 | 20 | 20 | 20 | 20
Cost | 3890 | 4225 | 2245 | 2000 | 440
Total cost: | 12800